## QUAD
Agency / Department |  |  | Contract ID |  |  | Project Title: |  |  | Project Manager: |  | Reporting Period:
SDLC
Project Planning |  | Start Date | End Date | Project Implementation |  |  | Start Date | End Date |  | Agency Logo
Initiation |  |  |  | Design
Concept |  |  |  | Develop
Planning |  |  |  | Test
Requirements |  |  |  | Implementation
Successes | [5 empty] | Health Check (RYG)
[6 empty] | Periods | Scope | Schedule | Costs | Risk / Issues | Quality | Resources
[6 empty] | Current | G | G | G | G | G | G
xx/yyyy
xx/yyyy
xx/yyyy
xx/yyyy
Changes & Impact | [5 empty] | Milestones
[6 empty] | Date | Milestone |  |  | Status* | Comment
Risks & Showstoppers
Description |  |  | Mitigation
* C = Complete IP = In Progress NS = Not Started
Open Items / Issues Needing Attention
Budget (in 000's)
Period | Appropriated | Actual Spent | ETC | EAC | Variance
Prior FY's | 0 | 0
Current FY (FY18) | 0 | 0
FY YTD | 0 | 0
Future FY's
- Add comments here
- Add comments here
- Add comments here
- Add comments here
- Add comments here

## Health Check
Health Status | Red | Yellow | Green
| (Critical) | (Caution) | (Controlled)
Scope | Planned value of change orders is greater than the earned value of the in scope work completed to date | Planned value of new change orders is greater than the earned value of the in scope work completed in the current period | Planned value of new change orders is less than the earned value of the in scope work achieved in the current period
Schedule | Critical path tasks, milestones and/or deliverables are more than 2 weeks overdue and corrective actions aren't likely to recover lost time | Critical path tasks, milestones and/or deliverables are more than 2 weeks overdue and corrective actions are likely to recover lost time | Critical path tasks, milestones and or deliverables are completed as scheduled or are estimated to be completed on time
Costs | Estimated cost at completion is greater than budgeted cost at completion | Estimated cost at completion is less than or equal to budgeted cost at completion, but cost performance index is less than 1 for more than 2 consecutive months | Estimated cost at completion is less than or equal to budgeted cost at completion, and cost performance index consistently is less than 1
Risk / Issues | There are 5 or more identified risks with a priority greater than 5 | There are less than 5 identified risks with a priority greater than 5 | There are no identified risks with a priority greater than 5
Quality | One or more deliverables are currently not approved due to quality issues and delaying the project schedule. | Quality issues are developing, as deliverable reviews are taking longer than scheduled due to a significant volume of adjustments. | Quality processes defined in the PMBOK or in Quality Management Plan are being followed.
| Quality processes defined in the PMBOK or Quality Management Plan aren't being followed. | Quality processes defined in the PMBOK or Quality Management Plan aren't being followed. | Deliverables are reviewed and approved on time with minimal adjustments.
Resources | Lack of resource availability and/or skills variance is delaying the project and jeopardizing the project's success | Lack of resource availability and/or skills variance are beginning to affect the team's ability to complete project tasks. | Necessary resources with adequate skills are available as needed.