## Bid Sheet
TORFP #: 601B1400004 Site: Mount Savage
# | Project Line Item | Price
A | Site Preparation Work
1 | Survey and mark the Limits of Disturbance (LOD) in accordance with the attached construction drawings
2 | Clearing and grading.
3 | Furnish and install sediment and erosion control systems and all storm water management features in accordance with the attached drawings.
4 | Furnish and install a stabilized construction entrance in accordance with the construction drawings.
5 | Furnish and install all storm water management systems in accordance with the attached drawings.
6 | Construct the tower foundation per tower manufacturer’s specifications.
7 | Constructtwo (2) 12x38ft. equipment shelter foundations.
8 | Construct one (1) 4x20ft. Concrete foundation for one (1) 1,000 gallon LP fuel tank.
9 | Install tower and shelter ground rings per the latest version of Motorola R56 installation standards.
10 | Upon completion of tower, shelter and site improvements, the TO Contractor will furnish and install surface materials in accordance with Attachment #22 a-f Construction Drawings. TO Contractor shall restore all areas of grass or existing pavement which have been disturbed during construction.
11 | Install an eight (8) ft. high-galvanized chain link fence with two (2) feet of barbed wire on top, with a twenty- four (24) ft. wide, double leaf vehicle gate; and two (2) five (5) foot man gates around the site (includes tower, equipment shelter and additional shelter foundation) as shown on Attachment #22a-f Construction Drawings.
B | Installation
12 | Purchase and delivery of one (1) fully functional, 330 ft. above ground level, three (3) legged, solid legged, heavy duty, self-supporting, two-way microwave radio tower.
13 | Tower Erection
14 | The TO Contractor shall purchase and install tower lighting equipment on the 330 ft. tower (Total finished height of the tower including all appurtenances will be 348 ft.) as per FAA Advisory Circular AC70/7460-1-G or latest revision.
15 | Purchase and installation of one (1) 12x38x10 ft. concrete equipment shelter (height is inside dimension) with a 75kW generator.
16 | Purchase and installation of one (1) new 1,000 gallon LP fuel tank with hookup to the generator and shall include first LP fill-up.
17 | Purchase and install one (1) extruded metal, 24-inch wide, no cantilever ice-bridge.
18 | Purchase and installation, per local utility standard, of an electrical backboard of steel post and unistrut construction to include CT cabinet, wire trough, main disconnect, at least one (1) electric company approved meter socket with room to accommodate a minimum of three (3) additional meters.
19 | Purchase and installation of conduits per specifications.
20 | Purchase and connection of electrical wiring.
21 | Supply bollards in accordance with the attached construction drawings.
Total Evaluated Price:
Submitted by:
| Authorized Signature | Title
| Printed Name of Authorized Signature | Federal Employer Number
| Company | Date
| Phone # | Address
SUBMIT COMPLETED DOCUMENT AS A PDF WITH SIGNATURE